## 00_README
CGI-ISO-001 — ISO/IEC 27001:2022 Readiness Assessment & Statement of Applicability
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Item | Detail
Purpose | Readiness assessment and 93-control Statement of Applicability for Cypher Group Inc., tracing every control to CGI-RSK-001 v1.1, CGI-GAP-001 and CGI-TPR-001.
Case-study notice | All organisations, people, findings, scores, dates and costs are invented for a portfolio. Real product names are stand-ins; any assurance status attributed to them is invented. ISO wording is paraphrased.
Sheets | 01_Scope · 02_SoA · 03_SoA_Summary · 04_Clauses · 05_DocInfo · 06_Readiness · 07_Roadmap · 08_REC_Reconciliation · 09_GAP_Impact · 10_Assumptions · 11_Issue_Checklist · 12_Lists
How status works | 02_SoA column N (maturity 0-4, yellow) drives column F (status, grey formula): 0 = Not started; 1-2 = Partial; 3-4 = Implemented; Applicable = N gives N/A - excluded. Column S checks maturity is not above the highest related CGI-GAP-001 Category score (09_GAP_Impact).
How the score works | 06_Readiness: 0.6 x clause score (04_Clauses) + 0.4 x Annex A score (03_SoA_Summary). Any failed gate (04_Clauses column K) forces NO-GO.
Colour legend - yellow | Input you may change (maturity, applicability, clause scores, weights, costs, document status)
Colour legend - grey | Formula - do not overwrite
Colour legend - green | Pass / met / implemented / worked example
Colour legend - red | Fail / absent / not started / zero
Colour legend - amber | Partial / condition
GitHub upload | Folder 05-iso27001-readiness-soa/ : this workbook, the .md, the .csv and data/*.csv. Create folders by typing the path in the file-name box (for example 05-iso27001-readiness-soa/data/05-clause-readiness.csv).
Notion upload | Import the CSVs, not this workbook: Settings > Import > CSV. Set Theme, Applicable, Status and Owner to Select; Maturity to Number.
Verification | Recalculated in LibreOffice before delivery with zero formula errors; counts cross-checked in code (see 11_Issue_Checklist).

## 01_Scope
ISMS scope statement and boundary
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Certificate wording | The information security management system supporting the development, operation, hosting and support of the Cypher Group Inc. cloud-based project-management software-as-a-service platform provided to business customers, including the people, processes and technology at its head office [address per assumption ISO-A01] and in its third-party cloud hosting environment, in accordance with the Statement of Applicability version 1.0.
Dimension | In scope | Out of scope, and why
Organisation | All 50 employees and all six functions | Nothing - at 50 people every function touches customer or platform data
Locations | Head office (ISO-A01); remote and home working under CGI-POL-001 section 4.4 | No data centre operated; production physical controls are AWS's, assured through A.5.23
Technology | AWS production (eu-central-1; backups us-east-1); GitHub; Google Workspace (IdP); Slack; Auth0; Datadog; Stripe integration; BYOD endpoints accessing company data | Vendors' internal controls - managed as interfaces through A.5.19-A.5.23 and CGI-TPR-001
Information | Customer account data and project content (~200 customers); payment metadata; internal documents; employee data; limited personal data | Cardholder numbers - none held (CGI-POL-004 section 4.1.4, AVD-001)
Processes | CGI-POL-001 to -005, CGI-RSK-001, CGI-TPR-001, CGI-ISO-001 | None
Interfaces (4.3 c) | 17 vendors CGI-VEN-001 to -017 (Tier 1/2/3 = 7/6/4); AWS shared-responsibility boundary (ISO-02) | -

## 02_SoA
Statement of Applicability - all 93 Annex A controls
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Columns A-L are the mandated SoA columns in the required order; M onward are governance columns.
Control | Title | Theme | Applicable Y/N | Justification for inclusion or exclusion | Implementation status | Evidence held or required | Owner (job title) | Related CGI-RSK-001 v1.1 risk ID | Related CGI-GAP-001 Category | Related CGI-TPR-001 finding | Target date | Basis for inclusion | Control maturity (0-4) | In CGI-GAP-001 mapping (Y/N) | CGI-GAP-001 mapped under | Roadmap link | Status points (Annex A score) | Maturity consistency check | Related Cat 1 | Related Cat 2 | Related Cat 3 | Max related Category score
A.5.1 | Policies for information security | Organizational | Y | Required by every register risk that relies on a written rule. Five topic-specific policies are approved (GV.PO = 2) but there is no top-level ISMS policy, 40% of staff have not acknowledged the pack and no annual review has run. | Partial | Held: CGI-POL-001 to -005 v1.0 approved; CGI-TRK-001 (60% acknowledged). Required: CEO-approved ISMS policy; first annual review record; 100% acknowledgement. | Chief Executive Officer | R-001; R-002 | GV.PO; GV.OC; GV.RM | - | 31 Oct 2026 | Risk + Maturity gap | 2 | Y | GV.OC; GV.RM; GV.PO | ISO-03; REC-04 | 0.5 | PASS | GV.PO | GV.OC | GV.RM | 2
A.5.2 | Information security roles and responsibilities | Organizational | Y | Accountability exists per document (GV.RR = 2) and CGI-POL-005 section 4 names response roles, but no ISMS role, security programme lead or RACI across the controls exists. | Partial | Held: document control blocks; CGI-POL-005 section 4 roles; CGI-TPR-001 RACI. Required: ISMS RACI covering this SoA; written assignment of the security programme lead. | Chief Executive Officer | R-003 | GV.RR | - | 31 Oct 2026 | Risk + Maturity gap | 2 | Y | GV.RR | ISO-04 | 0.5 | PASS | GV.RR |  |  | 2
A.5.3 | Segregation of duties | Organizational | Y | Policy approval is segregated (CGI-POL-002 approver moved to the CEO), but engineers can commit straight to production with no second person, which is the code-path duty conflict behind R-004. | Partial | Held: CGI-POL-002 approval record. Required: segregation-of-duties matrix; GitHub branch protection requiring a second reviewer. | Chief Technology Officer | R-004; R-003 | GV.RR | - | 31 Mar 2027 | Risk + Maturity gap | 1 | Y | GV.RR | REC-06 | 0.5 | PASS | GV.RR |  |  | 2
A.5.4 | Management responsibilities | Organizational | Y | Management must require staff to apply policy. CGI-TRK-001 shows 60% acknowledgement, so roughly 20 staff are bound by rules they have not read (GAP-004). | Partial | Held: CGI-TRK-001. Required: onboarding acknowledgement gate; CEO communication requiring compliance. | Chief Executive Officer | R-001; R-002 | GV.RR; GV.RM; GV.OC | - | 31 Dec 2026 | Risk + Maturity gap | 1 | Y | GV.OC; GV.RM; GV.RR | REC-04 | 0.5 | PASS | GV.RR | GV.RM | GV.OC | 2
A.5.5 | Contact with authorities | Organizational | Y | CGI-POL-005 section 5.6.3 commits to the GDPR 72-hour notification, but no lead supervisory authority or contact route is recorded (GAP-019), and F-002 shows the clock can start outside CGI's control. | Partial | Held: CGI-POL-005 section 5.6.3. Required: authority contact register (supervisory authority, national CSIRT, police cyber unit). | Head of Customer Success | VR-004; R-005; R-003 | RS.CO; RC.CO | F-002 (no vendor breach-notification clause) | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 1 | Y | RS.CO; RC.CO | ISO-01; REC-14 | 0.5 | PASS | RS.CO | RC.CO |  | 2
A.5.6 | Contact with special interest groups | Organizational | Y | Mapped by CGI-GAP-001 to RS.CO and RC.CO. No membership of any security community exists; also the practical feed for A.5.7. | Not started | Held: none. Required: record of at least one membership (for example a national CERT advisory list or an OWASP chapter). | Chief Technology Officer | - | RS.CO; RC.CO | - | 30 Jun 2027 | Maturity gap | 0 | Y | RS.CO; RC.CO | REC-12 | 0 | PASS | RS.CO | RC.CO |  | 2
A.5.7 | Threat intelligence | Organizational | Y | ID.RA = 3 describes the register method, not threat intelligence. The register's coverage rests on workshop judgement with no technical or threat input (CG-02), so this control is Not started. | Not started | Held: none. Required: named intelligence sources, a monthly review record and evidence that findings fed CGI-RSK-001. | Chief Technology Officer | R-001; R-002; R-004 | ID.RA; PR.PS | - | 31 Mar 2027 | Risk + Maturity gap | 0 | Y | ID.RA | REC-08 | 0 | PASS | ID.RA | PR.PS |  | 3
A.5.8 | Information security in project management | Organizational | Y | Missed by CGI-GAP-001. Features reach production with no security requirement step (R-004), and two AI tools entered the business with no project review (VR-005). | Not started | Held: none. Required: security requirements gate in CGI-POL-007; project intake checklist. | Chief Technology Officer | R-004; VR-005 | PR.PS | CGI-VEN-012 and -013 adopted outside any project or procurement review | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | N | - | REC-06 | 0 | PASS | PR.PS |  |  | 0
A.5.9 | Inventory of information and other associated assets | Organizational | Y | ID.AM = 1. The CGI-TPR-001 vendor inventory is one input; no inventory of AWS data stores, repositories, drives or endpoints exists. | Partial | Held: CGI-TPR-001 vendor inventory (17 rows). Required: asset and SaaS inventory with owner and CGI-POL-004 label per asset. | IT Operations Manager | R-003; R-005 | ID.AM | 17-vendor inventory (input only - not an asset inventory) | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 1 | Y | ID.AM | REC-05 | 0.5 | PASS | ID.AM |  |  | 1
A.5.10 | Acceptable use of information and other associated assets | Organizational | Y | CGI-POL-001 is approved, including section 4.5 on AI use, but 40% of staff have not acknowledged it and Otter.ai shows it being bypassed (VR-006). | Partial | Held: CGI-POL-001 v1.0. Required: 100% acknowledgement; AI-use briefing record. | Head of People and Operations | R-001; R-003; VR-006 | ID.AM; GV.PO | CGI-VEN-012 Otter.ai used in breach of CGI-POL-001 section 4.5 | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | ID.AM | REC-04 | 0.5 | PASS | ID.AM | GV.PO |  | 2
A.5.11 | Return of assets | Organizational | Y | Missed by CGI-GAP-001. The rule is written: CGI-POL-001 section 4.11 requires devices, access cards and printed material back within five business days, and CGI-POL-003 section 4.5.9 requires a completed offboarding checklist for every leaver. Neither has been evidenced, and neither reaches company data held on BYOD devices or in non-federated vendor accounts. | Partial | Held: CGI-POL-001 section 4.11; CGI-POL-003 sections 4.5.2 and 4.5.9. Required: completed offboarding checklists covering asset and data return and every non-federated vendor (CGI-TPR-001 Gate C). | Head of People and Operations | R-003; VR-008 | PR.AA | F-003 (no SCIM on Slack; leaver removal manual) | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | N | - | ISO-11; REC-02 | 0.5 | PASS | PR.AA |  |  | 2
A.5.12 | Classification of information | Organizational | Y | CGI-POL-004 defines four tiers (confirmed, VA-01), but the scheme has not been applied to any asset (ID.AM = 1). | Partial | Held: CGI-POL-004 v1.0. Required: classification recorded against every inventory entry; approved section 4.2 amendment. | Chief Technology Officer | R-003; R-005 | ID.AM; PR.DS | CGI-POL-004 section 4.2 named no third-party destinations (CGI-TPR-001 section 1.1) | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 2 | Y | ID.AM; PR.DS | REC-05 | 0.5 | PASS | ID.AM | PR.DS |  | 2
A.5.13 | Labelling of information | Organizational | Y | No asset carries a classification label, so the Handling Matrix cannot be enforced (GAP-007). | Partial | Held: labelling rules in CGI-POL-004. Required: labels applied in Google Workspace, repositories and data stores. | IT Operations Manager | R-003 | ID.AM | - | 31 Mar 2027 | Risk + Maturity gap | 1 | Y | ID.AM | REC-05 | 0.5 | PASS | ID.AM |  |  | 1
A.5.14 | Information transfer | Organizational | Y | The CGI-POL-004 Handling Matrix governs transfer, but it named no permitted third-party destinations until the CGI-TPR-001 amendment, which is still awaiting approval. | Partial | Held: CGI-POL-004 section 4.2. Required: CTO-approved amendment listing permitted destinations by classification. | Chief Technology Officer | R-003; VR-001; VR-003; VR-006 | PR.DS | F-001; F-004; CGI-POL-004 section 4.2 named no third-party destinations | 31 Oct 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | PR.DS | ISO-09 | 0.5 | PASS | PR.DS |  |  | 2
A.5.15 | Access control | Organizational | Y | CGI-POL-003 is an approved access control policy (PR.AA = 2). It has never been evidenced operating, and the four-hour SLA cannot be met on non-federated vendors. | Partial | Held: CGI-POL-003 v1.0. Required: first quarterly review record; SSO coverage list. | IT Operations Manager | R-001; R-003; VR-008 | PR.AA | F-003 | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | PR.AA | REC-02 | 0.5 | PASS | PR.AA |  |  | 2
A.5.16 | Identity management | Organizational | Y | Google Workspace is the identity provider (VRA addendum step 3), but Slack, Notion, Grammarly and Miro are not federated, so identity lifecycle is incomplete. | Partial | Held: CGI-POL-003 JML process. Required: SSO/SCIM on Tier 1 vendors (Slack by 15 Nov 2026); KRI-V5 at 100%. | IT Operations Manager | R-001; R-003; VR-008 | PR.AA | F-003; KRI-V5 | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | PR.AA | REC-01; VRA-2026-002 R3 | 0.5 | PASS | PR.AA |  |  | 2
A.5.17 | Authentication information | Organizational | Y | CGI-POL-002 sections 4.3 and 4.5 are strong, but MFA enrolment is 80% and ACC-001 still accepts SMS until 03 Mar 2027. | Partial | Held: CGI-POL-002; CGI-TRK-001 (80% MFA); ACC-001. Required: 100% enrolment report; ACC-001 retired. | IT Operations Manager | R-001 | PR.AA | F-010 (root-account MFA CUEC unaccepted) | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | PR.AA | REC-01 | 0.5 | PASS | PR.AA |  |  | 2
A.5.18 | Access rights | Organizational | Y | The CGI-POL-003 section 4.7.1 quarterly privileged review is mandated but has never run; the AWS report assumes CGI performs this review (CUEC). | Partial | Held: CGI-POL-003 section 4.7.1. Required: dated, signed quarterly review records (four by Stage 2). | IT Operations Manager | R-003; R-005; VR-008 | PR.AA | F-010 (least-privilege review CUEC); F-003 | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | PR.AA | REC-02; VRA-2026-001 C1 | 0.5 | PASS | PR.AA |  |  | 2
A.5.19 | Information security in supplier relationships | Organizational | Y | CGI-TPR-001 is the supplier process, so GV.SC = 2 (designed, owned, communicated). It is not 3: no review cycle has run on cadence, and the first Tier 1 re-reviews fall due Sep 2027. | Partial | Held: CGI-TPR-001 v1.0; VRA-2026-001/-002/-003. Required for Implemented: seven Tier 1 review records; four quarterly shadow-IT reconciliations; KRI reports. | Chief Technology Officer | VR-001; VR-002; VR-003; VR-004; VR-005; VR-006; VR-007; VR-008; VR-009; R-005 | GV.SC | Estate 17 vendors vs 5 known; 2 AI tools found only through expense claims, with no company contract; 4 of 17 with no assurance artifact | 30 Sep 2027 | Risk + Maturity gap + Vendor finding | 2 | Y | GV.SC | REC-15 (delivered) | 0.5 | PASS | GV.SC |  |  | 2
A.5.20 | Addressing information security within supplier agreements | Organizational | Y | The 18-clause checklist and Gate B (no DPA, no onboarding) are designed. 6 of 17 vendors still have no executed DPA, which is a live GDPR Article 28 gap and a likely Stage 2 finding if still open. | Partial | Held: CGI-TPR-001 section 7.4 checklist; 11 executed DPAs. Required: six outstanding DPAs executed; KRI-V1 at 100%. | Chief Technology Officer | VR-001; VR-004; VR-006; VR-007 | GV.SC | F-001; F-002; F-004; F-005; F-009 (no audit right - accepted); KRI-V1 = 65% (6 of 17 vendors with no DPA) | 31 Oct 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | GV.SC | ISO-09; VRA-2026-002 R1-R2 | 0.5 | PASS | GV.SC |  |  | 2
A.5.21 | Managing information security in the ICT supply chain | Organizational | Y | Questionnaire domain 7 and clauses 4-5 design the ICT supply-chain control, but fourth parties behind carve-out reports have never been reconciled. | Partial | Held: CGI-TPR-002 VQ-33 to VQ-36. Required: CSOC reconciliation records for AWS and Slack. | Chief Technology Officer | VR-003; VR-004 | GV.SC | F-007; F-011 (CSOC lists never reconciled) | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | GV.SC | VRA-2026-001 C2; VRA-2026-002 R6 | 0.5 | PASS | GV.SC |  |  | 2
A.5.22 | Monitoring, review and change management of supplier services | Organizational | Y | Review cadence is defined (12/18/24 months) and clause 9 treats assurance decay, but zero scheduled reviews have run and no change feed is monitored. | Partial | Held: CGI-TPR-001 tiering model and KRIs. Required: dated review records; sub-processor change-feed subscriptions. | Chief Technology Officer | VR-003; VR-009 | GV.SC | F-006 (stale Slack SOC 2); F-012 (sub-processor feed not subscribed) | 30 Sep 2027 | Risk + Maturity gap + Vendor finding | 2 | Y | GV.SC | VRA-2026-001 C2; REC-15 | 0.5 | PASS | GV.SC |  |  | 2
A.5.23 | Information security for use of cloud services | Organizational | Y | Cloud acquisition is covered by CGI-TPR-001, but there is no cloud-specific process, no documented shared-responsibility boundary and no tested exit, and the four CUECs are unaccepted, so the AWS opinion does not yet cover CGI's use. | Partial | Held: VRA-2026-001. Required: signed CUEC acceptance (C1); shared-responsibility statement; exit plan for Tier 1 cloud vendors (KRI-V7). | Chief Technology Officer | R-005; VR-002; VR-004; VR-007 | GV.SC; PR.IR | VRA-2026-001 AWS PASS WITH CONDITIONS (F-010 to F-013; all four conditions are CGI's) | 15 Dec 2026 | Risk + Maturity gap + Vendor finding | 1 | Y | GV.SC | ISO-02; VRA-2026-001 C1-C4 | 0.5 | PASS | GV.SC | PR.IR |  | 2
A.5.24 | Information security incident management planning and preparation | Organizational | Y | CGI-POL-005 is an approved plan with SEV1-SEV4, roles and targets (RS.MA = 2), but it has never been exercised and names no out-of-band channel. | Partial | Held: CGI-POL-005 v1.0. Required: tabletop record; vendor incident contacts; out-of-band channel. | Chief Technology Officer | R-002; R-005; VR-004 | RS.MA; RS.CO | F-002; VR-002 (out-of-band incident channel needed) | 30 Jun 2027 | Risk + Maturity gap + Vendor finding | 2 | Y | RS.MA; RS.CO | REC-12 | 0.5 | PASS | RS.MA | RS.CO |  | 2
A.5.25 | Assessment and decision on information security events | Organizational | Y | SEV bands exist, but with no telemetry and no alert-to-incident escalation, there is nothing to assess (DE.AE = 1). | Partial | Held: CGI-POL-005 SEV definitions. Required: written triage and escalation path; sample triage tickets. | IT Operations Manager | R-001; R-003 | DE.AE | - | 31 Mar 2027 | Risk + Maturity gap | 1 | Y | DE.AE | REC-07 | 0.5 | PASS | DE.AE |  |  | 1
A.5.26 | Response to information security incidents | Organizational | Y | The CGI-POL-005 section 5.5 response stages are written, but no containment runbooks exist and no response has ever been performed or rehearsed. | Partial | Held: CGI-POL-005 section 5.5. Required: runbooks for the top three scenarios; exercise record. | Chief Technology Officer | R-001; R-002; R-005; VR-004 | RS.MA; RS.MI | F-002; F-008 | 30 Jun 2027 | Risk + Maturity gap + Vendor finding | 2 | Y | RS.MA; RS.MI | REC-12 | 0.5 | PASS | RS.MA | RS.MI |  | 2
A.5.27 | Learning from information security incidents | Organizational | Y | The CGI-POL-005 sections 5.7 and 7.2 reviews and tabletop are written but have never run (ID.IM = 1). | Partial | Held: CGI-POL-005 sections 5.7 and 7.2. Required: lessons-learned record from the first tabletop. | Chief Technology Officer | R-002 | ID.IM; RS.AN | - | 30 Jun 2027 | Risk + Maturity gap | 1 | Y | ID.IM; RS.AN | REC-12 | 0.5 | PASS | ID.IM | RS.AN |  | 1
A.5.28 | Collection of evidence | Organizational | Y | CGI-POL-005 section 5.3.2 forbids deleting evidence, but no collection or chain-of-custody procedure or log retention standard sits beneath it. | Partial | Held: CGI-POL-005 sections 5.3.2 and 5.7.3. Required: evidence-handling procedure; 12-month log retention standard. | IT Operations Manager | R-003; R-004; VR-004 | RS.AN | F-008 (no customer-accessible Slack audit log) | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 1 | Y | RS.AN | REC-07 | 0.5 | PASS | RS.AN |  |  | 1
A.5.29 | Information security during disruption | Organizational | Y | There is no plan for maintaining security during disruption. Concentration means one AWS regional failure also removes monitoring, ticketing and runbooks. | Partial | Held: AWS snapshots only. Required: disruption plan naming the out-of-band tools; status page (CGI-VEN-017) live. | IT Operations Manager | R-002; VR-002 | RC.RP; RC.CO | VR-002 concentration: 5 vendors share AWS with the platform | 30 Jun 2027 | Risk + Maturity gap + Vendor finding | 1 | Y | RC.RP; RC.CO | REC-03; REC-14 | 0.5 | PASS | RC.RP | RC.CO |  | 1
A.5.30 | ICT readiness for business continuity | Organizational | Y | Backups exist but have never been restored, and no RTO or RPO is declared (CG-01). CGI-RSK-001 gives R-002 no backup credit until this closes. | Partial | Held: AWS native snapshots. Required: CGI-POL-006 with RTO/RPO; dated restore test report. | IT Operations Manager | R-002; VR-002; VR-007 | RC.RP | F-013 (no RTO/RPO, no restore test, export never exercised) | 15 Dec 2026 | Risk + Maturity gap + Vendor finding | 1 | Y | RC.RP | REC-03; VRA-2026-001 C4 | 0.5 | PASS | RC.RP |  |  | 1
A.5.31 | Legal, statutory, regulatory and contractual requirements | Organizational | Y | Obligations are scattered (GDPR processor role in assumption A-06, 72-hour duty in CGI-POL-005). No register of legal, regulatory and contractual requirements exists (GV.OC = 1). | Partial | Held: CGI-RSK-001 assumptions A-01 to A-06. Required: CEO-approved obligations register. | Chief Executive Officer | VR-001 | GV.OC | F-001 (GDPR Art. 28 non-conformity) | 31 Oct 2026 | Risk + Maturity gap + Vendor finding | 1 | Y | GV.OC | ISO-01 | 0.5 | PASS | GV.OC |  |  | 1
A.5.32 | Intellectual property rights | Organizational | Y | No register risk covers this, and it is not in CGI-GAP-001. Included because a SaaS company ships third-party and open-source code under licence terms, and the inventory shows tools bought on personal expenses (CGI-VEN-013). | Not started | Held: CGI-POL-001 section 4.6.2 bans unlicensed software on devices (a fragment). Required: software licence register; open-source licence rule in CGI-POL-007. | Chief Technology Officer | - | - | - | 30 Jun 2027 | Legal / regulatory - NOT risk-based | 0 | N | - | ISO-11 | 0 | No category |  |  |  | 0
A.5.33 | Protection of records | Organizational | Y | Missed by CGI-GAP-001, although CGI-POL-004 section 7 maps it. No retention standard exists for ISMS records or logs, and one Tier 1 vendor retains everything indefinitely. | Not started | Held: retention periods by tier in CGI-POL-004 section 4.2, and two record-specific rules (CGI-POL-003 section 4.7.4; CGI-POL-005 section 5.7.5). These are fragments: no schedule covers ISMS records, logs or contracts. Required: records and retention schedule (ISMS records, logs, contracts). | Chief Technology Officer | R-003; VR-004 | RS.AN | F-005 (Slack unlimited retention) | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | N | - | REC-07; ISO-08 | 0 | PASS | RS.AN |  |  | 1
A.5.34 | Privacy and protection of PII | Organizational | Y | Missed by CGI-GAP-001, although CGI is a GDPR processor for ~200 customers. Classification and breach duties exist, but there is no GDPR Article 30 record of processing and 6 vendors have no DPA. | Partial | Held: CGI-POL-004; CGI-POL-005 section 5.6.3. Required: GDPR Art. 30 record of processing; six DPAs; transfer register. | Chief Technology Officer | VR-001; VR-003; VR-006; R-003 | GV.OC; PR.DS | F-001; F-004; O-001; KRI-V1 = 65% | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 1 | N | - | ISO-09 | 0.5 | PASS | GV.OC | PR.DS |  | 2
A.5.35 | Independent review of information security | Organizational | Y | No independent review has ever taken place (GV.OV = 1). This assessment is internal and does not count. | Not started | Held: none. Required: independent internal audit report (ISO-12). | Chief Executive Officer | R-004; R-005 | GV.OV | - | 31 May 2027 | Risk + Maturity gap | 0 | Y | GV.OV | ISO-12 | 0 | PASS | GV.OV |  |  | 1
A.5.36 | Compliance with policies, rules and standards for information security | Organizational | Y | No compliance check against policy has ever run. Acknowledgement is 60% and KRIs have never been reported. | Partial | Held: CGI-TRK-001. Required: quarterly compliance check minuted at the REC-10 review. | Chief Technology Officer | R-001; R-002 | GV.PO; GV.OV | - | 31 Mar 2027 | Risk + Maturity gap | 1 | Y | GV.PO; GV.OV | REC-04; REC-10 | 0.5 | PASS | GV.PO | GV.OV |  | 2
A.5.37 | Documented operating procedures | Organizational | Y | Policies exist, but the procedures beneath them do not (GAP-017, GAP-020), and the planned runbook location shares AWS with the platform. | Partial | Held: policy pack only. Required: runbooks, stored where they survive a platform outage. | IT Operations Manager | R-002; R-005; VR-002 | GV.PO | CGI-VEN-011 Notion holds runbooks: no DPA, public links enabled, AWS-hosted | 30 Jun 2027 | Risk + Maturity gap + Vendor finding | 1 | Y | GV.PO | REC-12 | 0.5 | PASS | GV.PO |  |  | 2
A.6.1 | Screening | People | Y | Missed by CGI-GAP-001. CGI-POL-003 joiner steps exist (a weak mapping kept from Project 1), but no proportionate screening procedure is evidenced. | Partial | Held: CGI-POL-003 joiner section. Required: screening procedure lawful under EU/German employment law; sample records. | Head of People and Operations | R-003 | GV.RR | - | 31 Mar 2027 | Risk + Maturity gap | 1 | N | - | ISO-11 | 0.5 | PASS | GV.RR |  |  | 2
A.6.2 | Terms and conditions of employment | People | Y | Missed by CGI-GAP-001. No evidence that employment or contractor terms state information security responsibilities. | Not started | Held: none. Required: contract clause referencing the ISMS policy and CGI-POL-001. | Head of People and Operations | R-003 | GV.RR | - | 31 Dec 2026 | Risk + Maturity gap | 0 | N | - | ISO-11 | 0 | PASS | GV.RR |  |  | 2
A.6.3 | Information security awareness, education and training | People | Y | Induction only, 60% complete, with no recurring or role-based training and no phishing simulation (CG-04, PR.AT = 1). | Partial | Held: CGI-POL-003 section 4.3.6; CGI-TRK-001. Required: annual curriculum; simulation results; AI-use module. | Head of People and Operations | R-001; VR-005; VR-006 | PR.AT | VR-006: no staff instruction on CGI-POL-001 section 4.5 AI use | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 1 | Y | PR.AT | REC-09 | 0.5 | PASS | PR.AT |  |  | 1
A.6.4 | Disciplinary process | People | Y | Missed by CGI-GAP-001. No disciplinary procedure linked to policy breaches is on file, and unacknowledged policies are unenforceable (GAP-004). | Not started | Held: the sanction statement in each policy's Enforcement section (a fragment: there is no procedure behind it). Required: HR procedure referencing the CGI-POL pack. | Head of People and Operations | R-003; R-001 | GV.PO | - | 31 Dec 2026 | Risk + Maturity gap | 0 | N | - | ISO-11 | 0 | PASS | GV.PO |  |  | 2
A.6.5 | Responsibilities after termination or change of employment | People | Y | Missed by CGI-GAP-001. Leaver access removal is written; continuing confidentiality duties and vendor-account removal are not evidenced. | Partial | Held: CGI-POL-003 section 4.5.2. Required: leaver letter restating duties; vendor-account checklist. | Head of People and Operations | R-003; VR-008 | PR.AA | F-003; VR-008 | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 1 | N | - | ISO-11; REC-02 | 0.5 | PASS | PR.AA |  |  | 2
A.6.6 | Confidentiality or non-disclosure agreements | People | Y | Missed by CGI-GAP-001. No signed confidentiality agreements are on file for staff or contractors. | Not started | Held: none. Required: signed NDAs, reviewed annually (the control's own wording requires them documented). | Head of People and Operations | R-003; VR-003 | GV.RR | - | 31 Dec 2026 | Risk + Maturity gap | 0 | N | - | ISO-11 | 0 | PASS | GV.RR |  |  | 2
A.6.7 | Remote working | People | Y | Missed by CGI-GAP-001. CGI-POL-001 section 4.4 (BYOD) is an approved remote-working rule set, but there is no device register behind it. | Partial | Held: CGI-POL-001 section 4.4. Required: endpoint register; remote-working compliance check. | IT Operations Manager | R-001; R-003 | GV.PO; PR.AA | - | 31 Mar 2027 | Risk + Maturity gap | 2 | N | - | REC-05 | 0.5 | PASS | GV.PO | PR.AA |  | 2
A.6.8 | Information security event reporting | People | Y | CGI-POL-005 section 5.2 reporting channels are approved, but no event has been reported or rehearsed. | Partial | Held: CGI-POL-005 section 5.2. Required: incident register entries; tabletop record. | Chief Technology Officer | R-001; R-003; VR-004 | PR.AT; RS.CO | F-002 | 30 Jun 2027 | Risk + Maturity gap + Vendor finding | 2 | Y | PR.AT; RS.CO | REC-12 | 0.5 | PASS | PR.AT | RS.CO |  | 2
A.7.1 | Physical security perimeters | Physical | Y | No register risk covers physical intrusion, and physical security was out of CGI-GAP-001 scope. Applicable because the head office holds staff endpoints; enterprise questionnaires ask this (CGI asks it of vendors: VQ-64 to VQ-66). Candidate risk CR-03 is proposed rather than invented. | Not started | Held: none. Required: landlord security schedule (assumption ISO-A03). | IT Operations Manager | - | - | - | 31 Mar 2027 | Contractual / stakeholder - NOT risk-based | 0 | N | - | ISO-11 | 0 | No category |  |  |  | 0
A.7.2 | Physical entry | Physical | Y | As A.7.1. Building entry is assumed to be provided by the landlord and is not evidenced. | Not started | Held: none. Required: access badge process; visitor log. | IT Operations Manager | - | - | - | 31 Mar 2027 | Contractual / stakeholder - NOT risk-based | 0 | N | - | ISO-11 | 0 | No category |  |  |  | 0
A.7.3 | Securing offices, rooms and facilities | Physical | Y | As A.7.1. The office is in scope as a place where Confidential information is handled on screen. | Not started | Held: none. Required: office security rules. | IT Operations Manager | - | - | - | 31 Mar 2027 | Contractual / stakeholder - NOT risk-based | 0 | N | - | ISO-11 | 0 | No category |  |  |  | 0
A.7.4 | Physical security monitoring | Physical | N | EXCLUDED. There are no secure areas or on-premises information processing facilities: production runs in AWS, whose physical monitoring is assured through A.5.23 (VRA-2026-001). The serviced office holds only portable endpoints. Re-include if servers, network equipment or Confidential paper records are kept on site. | N/A - excluded | Held: VRA-2026-001 (AWS SOC 2 covers data-centre monitoring). Required: exclusion approved in SoA v1.0. | IT Operations Manager | - | - | - | N/A - re-evaluate at SoA review 30 Sep 2027 | Excluded | 0 | N | - | - |  | N/A |  |  |  | 0
A.7.5 | Protecting against physical and environmental threats | Physical | Y | No register risk covers this. It is applicable only to people and endpoints in the office (landlord fire and flood controls); production resilience is covered by A.5.23 and A.8.14. | Not started | Held: none. Required: landlord fire-safety confirmation. | IT Operations Manager | - | - | - | 30 Jun 2027 | Contractual / stakeholder - NOT risk-based | 0 | N | - | ISO-11 | 0 | No category |  |  |  | 0
A.7.6 | Working in secure areas | Physical | N | EXCLUDED. No secure areas are defined, because there is no server or network room. Re-include if one is created. | N/A - excluded | Held: n/a. Required: exclusion approved in SoA v1.0. | IT Operations Manager | - | - | - | N/A - re-evaluate at SoA review 30 Sep 2027 | Excluded | 0 | N | - | - |  | N/A |  |  |  | 0
A.7.7 | Clear desk and clear screen | Physical | Y | No register risk covers shoulder-surfing or unattended screens; included as a baseline expected by customers and auditors. The rule already exists: CGI-POL-001 sections 4.4.2 (automatic screen lock), 4.8.2 (no unattended Confidential printouts) and 4.9.3 (lock the device when stepping away), which CGI-POL-001 section 8 maps to A.7.7. It is approved but unevidenced, and 40% of staff have not acknowledged it. | Partial | Held: CGI-POL-001 sections 4.4.2, 4.8.2 and 4.9.3. Required: 100% acknowledgement; screen-lock configuration evidence; clear-desk spot-check record. | Head of People and Operations | - | - | - | 31 Dec 2026 | Contractual / stakeholder - NOT risk-based | 2 | N | - | ISO-11; REC-04 | 0.5 | No category |  |  |  | 0
A.7.8 | Equipment siting and protection | Physical | Y | No register risk covers this. Applicable to endpoints in the office and at home; included on a baseline and stakeholder basis. | Not started | Held: none. Required: guidance within the remote-working rules. | IT Operations Manager | - | - | - | 31 Mar 2027 | Contractual / stakeholder - NOT risk-based | 0 | N | - | ISO-11 | 0 | No category |  |  |  | 0
A.7.9 | Security of assets off-premises | Physical | Y | Relates to ID.AM (no endpoint register, score 1). CGI-POL-001 section 4.4 covers device use off-site. Candidate risk CR-01 (lost or stolen endpoint) is recommended for the register. | Partial | Held: CGI-POL-001 section 4.4. Required: endpoint register; full-disk encryption evidence. | IT Operations Manager | - | ID.AM | - | 31 Mar 2027 | Maturity gap | 1 | N | - | REC-05 | 0.5 | PASS | ID.AM |  |  | 1
A.7.10 | Storage media | Physical | Y | Missed by CGI-GAP-001. The CGI-POL-004 section 4.2 Handling Matrix governs removable media, and EXC-003 records an approved exception, so the rule is designed and exercised through the exception process. | Partial | Held: CGI-POL-004 section 4.2; EXC-003. Required: media usage record. | Chief Technology Officer | R-003 | PR.DS | - | 31 Mar 2027 | Risk + Maturity gap | 2 | N | - | - | 0.5 | PASS | PR.DS |  |  | 2
A.7.11 | Supporting utilities | Physical | N | EXCLUDED. No information processing facility is operated, so there are no utilities to protect. Power and cooling for production are AWS's responsibility, assured through A.5.23 (VRA-2026-001). | N/A - excluded | Held: VRA-2026-001. Required: exclusion approved in SoA v1.0. | IT Operations Manager | - | - | - | N/A - re-evaluate at SoA review 30 Sep 2027 | Excluded | 0 | N | - | - |  | N/A |  |  |  | 0
A.7.12 | Cabling security | Physical | N | EXCLUDED. There is no on-premises network cabling carrying production data. Office connectivity is the landlord's shared service, and platform networking is covered by A.8.20 to A.8.22. | N/A - excluded | Held: n/a. Required: exclusion approved in SoA v1.0. | IT Operations Manager | - | - | - | N/A - re-evaluate at SoA review 30 Sep 2027 | Excluded | 0 | N | - | - |  | N/A |  |  |  | 0
A.7.13 | Equipment maintenance | Physical | Y | No register risk covers this. Applicable to endpoints. The CGI-POL-001 section 4.4.3 patch rule is a software fragment, not maintenance, so it does not change the status. | Not started | Held: none. Required: endpoint maintenance and repair rule (data wiped before third-party repair). | IT Operations Manager | - | - | - | 30 Jun 2027 | Contractual / stakeholder - NOT risk-based | 0 | N | - | ISO-11 | 0 | No category |  |  |  | 0
A.7.14 | Secure disposal or re-use of equipment | Physical | Y | Relates to ID.AM (asset lifecycle, score 1). GDPR Article 32 requires secure disposal of personal data on retired devices. No procedure exists. | Not started | Held: none. Required: wipe or destruction record per retired device. | IT Operations Manager | - | ID.AM | - | 31 Mar 2027 | Maturity gap + Legal | 0 | N | - | REC-05 | 0 | PASS | ID.AM |  |  | 1
A.8.1 | User endpoint devices | Technological | Y | CGI-POL-001 section 4.4 BYOD rules exist, but there is no register and no management tooling for the 50 staff devices (ID.AM = 1). | Partial | Held: CGI-POL-001 section 4.4. Required: endpoint register; encryption and screen-lock compliance report. | IT Operations Manager | R-001; R-002; R-003 | ID.AM | - | 31 Mar 2027 | Risk + Maturity gap | 1 | Y | ID.AM | REC-05 | 0.5 | PASS | ID.AM |  |  | 1
A.8.2 | Privileged access rights | Technological | Y | CGI-POL-002 section 4.3.3 mandates phishing-resistant MFA for privileged accounts, but the CGI-POL-003 section 4.7.1 quarterly review has never run and the AWS root-account CUEC is unaccepted. | Partial | Held: CGI-POL-002 section 4.3.3. Required: privileged account list; quarterly review records; root MFA evidence. | IT Operations Manager | R-005; R-003; R-001 | PR.AA | F-010 (root MFA and least-privilege CUECs) | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | PR.AA | REC-02; VRA-2026-001 C1 | 0.5 | PASS | PR.AA |  |  | 2
A.8.3 | Information access restriction | Technological | Y | Missed by CGI-GAP-001, and the most important omission: R-004 is an application authorisation flaw, which is this control. No authorisation design standard or test exists (PR.PS = 0). CGI asks vendors for tenant isolation (VQ-24) that it cannot yet evidence itself. | Not started | Held: none. Required: authorisation and tenant-isolation design standard; test cases; REC-16 penetration test result. | Chief Technology Officer | R-004 | PR.PS; PR.AA | - | 31 Mar 2027 | Risk + Maturity gap | 0 | N | - | REC-06; REC-16 | 0 | PASS | PR.PS | PR.AA |  | 2
A.8.4 | Access to source code | Technological | Y | Missed by CGI-GAP-001. CGI-POL-002 section 4.5.2 secret scanning is a recorded fragment, but repository access and write rights are uncontrolled. Kept at Not started to agree with PR.PS = 0. | Not started | Held: CGI-POL-002 section 4.5.2 (fragment). Required: repository access review; branch protection configuration export. | Chief Technology Officer | R-004 | PR.PS | CGI-VEN-002 GitHub: Tier 1, inherent 15 Critical, no branch protection on the CGI side | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | N | - | REC-06 | 0 | PASS | PR.PS |  |  | 0
A.8.5 | Secure authentication | Technological | Y | MFA is mandated and 80% enrolled; ACC-001 accepts SMS until 03 Mar 2027. This is a brakes control: it acts before the break-in. | Partial | Held: CGI-TRK-001 (80%). Required: 100% enrolment export; phishing-resistant MFA on all admins. | IT Operations Manager | R-001 | PR.AA | F-003 (no SSO on Slack); F-010 | 31 Dec 2026 | Risk + Maturity gap + Vendor finding | 2 | Y | PR.AA | REC-01 | 0.5 | PASS | PR.AA |  |  | 2
A.8.6 | Capacity management | Technological | Y | No register risk covers capacity exhaustion, and CGI-GAP-001 does not map it. Included because ~200 customers depend on platform availability (assumption ISO-A04); CGI already asks this of its own vendors (VQ-55). Candidate risk CR-02 is proposed rather than invented. | Not started | Held: none. Required: capacity monitoring thresholds; quarterly capacity review. | Chief Technology Officer | - | - | - | 30 Jun 2027 | Contractual / stakeholder - NOT risk-based | 0 | N | - | ISO-11 | 0 | No category |  |  |  | 0
A.8.7 | Protection against malware | Technological | Y | No anti-malware standard covers the 50 BYOD endpoints (GAP-020). | Not started | Held: CGI-POL-001 section 4.2.3 forbids disabling endpoint protection (a fragment: nothing requires it to be installed or checks that it is). Required: endpoint protection standard; coverage report. | IT Operations Manager | R-002; R-001 | RS.MI | - | 31 Mar 2027 | Risk + Maturity gap | 0 | Y | RS.MI | ISO-11 | 0 | PASS | RS.MI |  |  | 1
A.8.8 | Management of technical vulnerabilities | Technological | Y | PR.PS = 0 and CG-02: no scanning, no remediation SLA, CGI-POL-008 unwritten. The endpoint patch rule (CGI-POL-001 section 4.4.3) is a fragment that does not cover the platform, so the status is Not started. | Not started | Held: CGI-POL-001 section 4.4.3 (fragment). Required: CGI-POL-008; authenticated scan reports; remediation tickets within SLA. | Chief Technology Officer | R-002; R-004 | PR.PS; ID.RA | CG-02 | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | ID.RA; PR.PS | REC-08 | 0 | PASS | PR.PS | ID.RA |  | 3
A.8.9 | Configuration management | Technological | Y | CG-03: there is no AWS configuration baseline and no drift detection (PR.IR = 0). This is the documented reason R-005 stays High. | Not started | Held: none. Required: CIS AWS Foundations baseline; posture-monitoring reports. | IT Operations Manager | R-005; R-004 | PR.PS; PR.IR | F-010; CG-03 | 30 Jun 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.PS; PR.IR | REC-11 | 0 | PASS | PR.PS | PR.IR |  | 0
A.8.10 | Information deletion | Technological | Y | Deletion is designed for vendor exits (clause 12, VQ-73) but not for CGI's own systems: no retention or deletion schedule has been executed (GAP-012). | Partial | Held: CGI-POL-004 section 4.2 retention limits and disposal methods (designed, never executed); CGI-TPR-001 clause 12. Required: retention and deletion schedule; deletion certificates. | Chief Technology Officer | R-003; VR-001; VR-006 | PR.DS | F-005; clause 12 (certified deletion) in CGI-TPR-001 section 7.4 | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 1 | Y | PR.DS | REC-17; ISO-08 | 0.5 | PASS | PR.DS |  |  | 2
A.8.11 | Data masking | Technological | Y | There is no masking of customer data in logs or lower environments; Project 1's mapping to the Handling Matrix was weak and is not credited. | Not started | Held: none. Required: masking rule for logs and test data; Datadog scrubbing configuration. | Chief Technology Officer | R-003; VR-004 | PR.DS | CGI-VEN-007 Datadog: log scrubbing rules not verified | 30 Jun 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.DS | ISO-11 | 0 | PASS | PR.DS |  |  | 2
A.8.12 | Data leakage prevention | Technological | Y | CG-05: there is no data-loss prevention; monitoring is metadata-only. | Not started | Held: CGI-POL-001 section 4.5.2, a behavioural rule against entering Confidential data into unapproved AI tools (a fragment, not leakage prevention). Required: egress and DLP rules on Google Workspace and GitHub; alert samples. | Chief Technology Officer | R-003 | PR.DS; DE.CM | VR-006 (AI tools reading typed text) | 30 Sep 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.DS; DE.CM | REC-17 | 0 | PASS | PR.DS | DE.CM |  | 2
A.8.13 | Information backup | Technological | Y | Seatbelt, not brakes: backup acts after the bang, limiting the impact of R-002 ransomware. Snapshots exist but have never been restored (CG-01), so no credit is taken. | Partial | Held: AWS snapshot configuration. Required: CGI-POL-006; dated restore test to a clean environment; six-monthly repeat. | IT Operations Manager | R-002; VR-002 | PR.IR; RC.RP | F-013; VRA-2026-001 C4 | 15 Dec 2026 | Risk + Maturity gap + Vendor finding | 1 | Y | PR.IR; RC.RP | REC-03 | 0.5 | PASS | PR.IR | RC.RP |  | 1
A.8.14 | Redundancy of information processing facilities | Technological | Y | No redundancy design is documented for the platform. The status-page placement is a design-time fragment only. | Not started | Held: none. Required: availability architecture record (zones and regions); failover test. | Chief Technology Officer | R-002; VR-002 | PR.IR | VR-002; CGI-VEN-017 deliberately hosted off AWS | 30 Jun 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.IR | ISO-11 | 0 | PASS | PR.IR |  |  | 0
A.8.15 | Logging | Technological | Y | Some logs exist ad hoc (application logs in Datadog), but organisation-wide CloudTrail is unverified and there is no central security log or retention (DE.CM = 1). | Partial | Held: Datadog APM (engineering use). Required: CloudTrail with validation; central log account; retention standard. | IT Operations Manager | R-003; R-005; VR-004 | DE.CM; DE.AE; RS.AN | F-008; F-010 (CloudTrail CUEC); CGI-VEN-007 not a security log source | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 1 | Y | DE.CM; DE.AE; RS.AN | REC-07 | 0.5 | PASS | DE.CM | DE.AE | RS.AN | 1
A.8.16 | Monitoring activities | Technological | Y | There is no alerting on root use, IAM change, public S3 or mass download (GAP-015). | Not started | Held: CGI-POL-001 section 4.10 monitoring notice (a fragment: it tells staff monitoring may occur, but no alert exists). Required: alert rules; alert-handling records. | IT Operations Manager | R-003; R-005 | DE.CM; DE.AE | F-010 | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | DE.CM; DE.AE | REC-07 | 0 | PASS | DE.CM | DE.AE |  | 1
A.8.17 | Clock synchronization | Technological | Y | Missed by CGI-GAP-001. A supporting control: logs without a common time source cannot support A.5.28 investigations. The provider time source is assumed but not verified. | Not started | Held: none. Required: configuration evidence of a common time source. | IT Operations Manager | R-003; VR-004 | DE.CM; RS.AN | - | 31 Mar 2027 | Risk + Maturity gap | 0 | N | - | REC-07 | 0 | PASS | DE.CM | RS.AN |  | 1
A.8.18 | Use of privileged utility programs | Technological | Y | Missed by CGI-GAP-001. Administrative tooling with broad IAM rights is unrestricted and unrecorded. | Not started | Held: none. Required: list of privileged tools and who may use them. | IT Operations Manager | R-005; R-003 | PR.AA | - | 30 Jun 2027 | Risk + Maturity gap | 0 | N | - | REC-11 | 0 | PASS | PR.AA |  |  | 2
A.8.19 | Installation of software on operational systems | Technological | Y | Missed by CGI-GAP-001. Software reaches production with no controlled release process (PR.PS = 0). | Not started | Held: CGI-POL-001 section 4.6.2 (an endpoint software rule; a fragment that does not reach production). Required: release procedure in CGI-POL-007; deployment pipeline records. | Chief Technology Officer | R-004; R-002 | PR.PS | - | 31 Mar 2027 | Risk + Maturity gap | 0 | N | - | REC-06 | 0 | PASS | PR.PS |  |  | 0
A.8.20 | Networks security | Technological | Y | There is no network security baseline (CG-03, PR.IR = 0). | Not started | Held: none. Required: security-group and VPC baseline; review record. | IT Operations Manager | R-005 | PR.IR | - | 30 Jun 2027 | Risk + Maturity gap | 0 | Y | PR.IR | REC-11 | 0 | PASS | PR.IR |  |  | 0
A.8.21 | Security of network services | Technological | Y | Missed by CGI-GAP-001. Security requirements for the network services consumed (VPC, DNS, TLS endpoints) are not defined. | Not started | Held: none. Required: network service requirements; provider evidence mapped. | IT Operations Manager | R-005; VR-004 | PR.IR | - | 30 Jun 2027 | Risk + Maturity gap | 0 | N | - | REC-11 | 0 | PASS | PR.IR |  |  | 0
A.8.22 | Segregation of networks | Technological | Y | Segmentation is undocumented (GAP-014). The remediation stays at Q4 2027 in the risk treatment plan; the boundary documentation moves forward into ISO-02. | Not started | Held: none. Required: segmentation diagram; production access boundary. | IT Operations Manager | R-005; R-004 | PR.IR | - | 31 Dec 2027 | Risk + Maturity gap | 0 | Y | PR.IR | REC-18 (split - see RC-04) | 0 | PASS | PR.IR |  |  | 0
A.8.23 | Web filtering | Technological | Y | Missed by CGI-GAP-001. There is no web filtering on BYOD endpoints; a DNS-filtering option is proposed. | Not started | Held: none. Required: filtering configuration; coverage report. | IT Operations Manager | R-001; R-002 | PR.PS | - | 30 Jun 2027 | Risk + Maturity gap | 0 | N | - | ISO-11 | 0 | PASS | PR.PS |  |  | 0
A.8.24 | Use of cryptography | Technological | Y | Seatbelt control: it reduces the impact of a stolen copy (VR-004). There is no encryption standard (GAP-012). Server-side encryption does NOT reduce the impact of a public-bucket misconfiguration (R-005), because the service decrypts for any request the misconfiguration allows. | Not started | Held: CGI-POL-004 section 4.2 says where encryption is required and CGI-POL-001 section 4.4.1 requires disk encryption on devices (fragments: no algorithms, TLS minimum or key management are defined). Required: cryptography standard (algorithms, TLS minimum, key management); KMS configuration. | Chief Technology Officer | VR-004; R-005 | PR.DS | F-010 (encryption-management CUEC) | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.DS | ISO-11 | 0 | PASS | PR.DS |  |  | 2
A.8.25 | Secure development life cycle | Technological | Y | PR.PS = 0 and CG-02: there is no secure development lifecycle and CGI-POL-007 is unwritten. | Not started | Held: none. Required: CGI-POL-007 approved; SDLC evidence per release. | Chief Technology Officer | R-004 | PR.PS | CG-02 | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.PS | REC-06 | 0 | PASS | PR.PS |  |  | 0
A.8.26 | Application security requirements | Technological | Y | Missed by CGI-GAP-001. No application security requirements are defined for features, including authorisation rules. | Not started | Held: none. Required: requirements template; sample completed per feature. | Chief Technology Officer | R-004 | PR.PS | - | 31 Mar 2027 | Risk + Maturity gap | 0 | N | - | REC-06 | 0 | PASS | PR.PS |  |  | 0
A.8.27 | Secure system architecture and engineering principles | Technological | Y | Missed by CGI-GAP-001. No secure architecture principles are documented; concentration on one provider was found only by drawing the dependency graph. | Not started | Held: CGI-TPR-001 section 2.5 dependency graph. Required: architecture principles; design review records. | Chief Technology Officer | R-004; R-005; VR-002 | PR.IR | VR-002 concentration | 31 Dec 2027 | Risk + Maturity gap + Vendor finding | 0 | N | - | REC-18; ISO-02 | 0 | PASS | PR.IR |  |  | 0
A.8.28 | Secure coding | Technological | Y | PR.PS = 0 and CG-02: there is no mandatory peer review, no branch protection and no coding standard. This is a brakes control: it stops the authorisation flaw being written in the first place. | Not started | Held: CGI-POL-002 section 4.5.2 secret scanning (a fragment). Required: coding standard; branch-protection export; review records. | Chief Technology Officer | R-004 | PR.PS | CG-02 | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.PS | REC-06; REC-16 | 0 | PASS | PR.PS |  |  | 0
A.8.29 | Security testing in development and acceptance | Technological | Y | PR.PS = 0 and CG-02: no SAST (static application security testing) and no penetration test. | Not started | Held: none. Required: SAST results in CI; annual penetration test report. | Chief Technology Officer | R-004 | PR.PS | CG-02 | 30 Sep 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.PS | REC-16 | 0 | PASS | PR.PS |  |  | 0
A.8.30 | Outsourced development | Technological | N | EXCLUDED. All development is performed by CGI employees (assumption ISO-A02). Re-include before any contractor or agency writes code. Supplier assurance for development tools (GitHub) is covered by A.5.19 to A.5.22. | N/A - excluded | Held: n/a. Required: exclusion approved in SoA v1.0. | Chief Technology Officer | - | - | - | N/A - re-evaluate at SoA review 30 Sep 2027 | Excluded | 0 | N | - | - |  | N/A |  |  |  | 0
A.8.31 | Separation of development, test and production environments | Technological | Y | PR.PS = 0 and CG-02: there is no recorded separation of development, test and production. | Not started | Held: none. Required: environment diagram; access separation evidence. | Chief Technology Officer | R-004; R-003 | PR.PS | - | 31 Mar 2027 | Risk + Maturity gap | 0 | Y | PR.PS | REC-06 | 0 | PASS | PR.PS |  |  | 0
A.8.32 | Change management | Technological | Y | PR.PS = 0 and CG-02: there is no change management policy or approval record. | Not started | Held: none. Required: CGI-POL-007 change section; change records. | Chief Technology Officer | R-004; R-005 | PR.PS | CG-02 | 31 Mar 2027 | Risk + Maturity gap + Vendor finding | 0 | Y | PR.PS | REC-06 | 0 | PASS | PR.PS |  |  | 0
A.8.33 | Test information | Technological | Y | Missed by CGI-GAP-001. There is no rule preventing production customer data being used in lower environments. | Not started | Held: none. Required: test-data rule; masked data set evidence. | Chief Technology Officer | R-003; R-004 | PR.DS | - | 31 Mar 2027 | Risk + Maturity gap | 0 | N | - | REC-06 | 0 | PASS | PR.DS |  |  | 2
A.8.34 | Protection of information systems during audit testing | Technological | Y | No register risk covers this. Included because the ISO-12 internal audit and the REC-16 penetration test will touch production; the rules must exist before either runs. | Not started | Held: none. Required: audit and test rules of engagement. | Chief Technology Officer | - | - | - | 30 Jun 2027 | Contractual / stakeholder - NOT risk-based | 0 | N | - | ISO-12; REC-16 | 0 | No category |  |  |  | 0

## 03_SoA_Summary
SoA summary (all formulas)
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Theme | Controls | Applicable | Excluded | Implemented | Partial | Not started | Check (sum = applicable)
Organizational | 37 | 37 | 0 | 0 | 31 | 6 | PASS
People | 8 | 8 | 0 | 0 | 5 | 3 | PASS
Physical | 14 | 10 | 4 | 0 | 3 | 7 | PASS
Technological | 34 | 33 | 1 | 0 | 6 | 27 | PASS
TOTAL | 93 | 88 | 5 | 0 | 45 | 43 | PASS
Annex A points (Implemented x1 + Partial x0.5) | 22.5
Annex A score | 25.57%
Maturity consistency FAILs | 0
Controls in CGI-GAP-001 mapping | 55
Controls CGI-GAP-001 missed | 38
Missed and applicable | 33
Applicable with a risk ID (risk-based) | 75
Applicable, NOT risk-based and untraced | 10
Maturity | Applicable controls
0 | 43
1 | 23
2 | 22
3 | 0
4 | 0
Owner (job title) | Applicable controls owned
Chief Executive Officer | 5
Chief Technology Officer | 39
Head of People and Operations | 9
IT Operations Manager | 34
Head of Customer Success | 1
Finance Manager | 0

## 04_Clauses
Clauses 4-10 readiness (score 0 absent / 1 partial / 2 met with evidence)
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Clause | Requirement | Stage 1 gate (Y/N) | Score (0-2) | Current state | Gap | Evidence needed | Owner (job title) | Action | Due | Gate failed? | Result
4.1 | Understand the organisation and its context: internal and external issues, including whether climate change is relevant (Amd 1:2024) | N | 1 | Context exists only as CGI-RSK-001 assumptions A-01 to A-06 (GV.OC = 1). | No approved context statement; climate change not considered. | Approved context and issues statement. | Chief Executive Officer | ISO-01 | 31 Oct 2026 | no | Partial
4.2 | Interested parties, their relevant requirements, and which of those the ISMS addresses | N | 1 | Customers, a GDPR supervisory authority and vendors are known across CGI-POL-005 and CGI-TPR-001. | No interested-parties register; no decision on which requirements the ISMS addresses. | Interested-parties and obligations register (with A.5.31). | Chief Executive Officer | ISO-01 | 31 Oct 2026 | no | Partial
4.3 | Determine and document the ISMS scope, considering interfaces and dependencies with other organisations | Y | 1 | Drafted in CGI-ISO-001 section 2 (this document). | Not approved by top management. | CEO-approved scope statement v1.0. | Chief Executive Officer | ISO-02 | 31 Oct 2026 | YES | Partial
4.4 | Establish, implement, maintain and continually improve the ISMS | N | 1 | Components exist (policies, register, gap assessment, vendor programme) but do not run as one system. | No ISMS manual or process map linking them. | ISMS overview showing how the clauses 4-10 processes connect. | Chief Technology Officer | ISO-08 | 31 Dec 2026 | no | Partial
5.1 | Leadership and commitment | N | 1 | The CEO approved CGI-POL-001 to -005, CGI-RSK-001, CGI-GAP-001 and CGI-TPR-001. | The USD 32,100 year-one budget is costed but unapproved (GAP-003); no stated commitment to the ISMS. | Approved budget; ISMS policy signed by the CEO. | Chief Executive Officer | ISO-03 | 31 Oct 2026 | no | Partial
5.2 | Information security policy: appropriate, provides a framework for objectives, commits to requirements and continual improvement; documented and communicated | N | 1 | Five topic-specific policies are approved. | No top-level ISMS policy meeting 5.2 a) to d). | ISMS policy v1.0, communicated and acknowledged. | Chief Executive Officer | ISO-03 | 31 Oct 2026 | no | Partial
5.3 | Roles, responsibilities and authorities, including for ISMS conformance and reporting to top management | N | 1 | Document-level owners exist (GV.RR = 2). | No one is assigned to ensure ISMS conformance or report its performance. | Written assignment of an ISMS lead; RACI. | Chief Executive Officer | ISO-04 | 31 Oct 2026 | no | Partial
6.1.1 | Determine risks and opportunities for the ISMS itself and plan actions | N | 0 | None. | ISMS-level risks and opportunities have never been considered (distinct from information security risks). | Short ISMS risks and opportunities record. | Chief Technology Officer | ISO-08 | 31 Dec 2026 | no | Absent
6.1.2 | Information security risk assessment process, including risk ACCEPTANCE criteria and criteria for performing assessments | Y | 1 | CGI-RSK-001 applies a documented NIST SP 800-30 5x5 method and has operated twice (v1.0, v1.1). ID.RA = 3. | No risk acceptance criteria or appetite (GAP-002), so ACC-001 and ACC-V01 were accepted against nothing. No defined re-assessment cadence. | CEO-approved risk acceptance criteria; assessment cadence. | Chief Executive Officer | ISO-05 (REC-13 pulled forward) | 31 Oct 2026 | YES | Partial
6.1.3 | Risk treatment: select options, determine controls, compare with Annex A, produce the SoA and a risk treatment plan, and obtain risk owners' approval and residual acceptance | Y | 1 | Four treatment options applied; TP-01 to TP-10 costed; SoA drafted here (93 controls). | SoA and consolidated RTP not approved; residual High risks (R-004, R-005, VR-004) not formally accepted by their owners. | Approved SoA v1.0; approved RTP; signed residual-risk acceptances. | Chief Executive Officer | ISO-06 | 30 Nov 2026 | YES | Partial
6.2 | Information security objectives: measurable, monitored, communicated; plans to achieve them | N | 0 | 14 KRIs exist in CGI-RSK-001 v1.1. | KRIs are indicators, not objectives. No objectives are set. | Objectives with owners, targets and dates. | Chief Technology Officer | ISO-07 | 30 Nov 2026 | no | Absent
6.3 | Planning of changes to the ISMS | N | 0 | None. | No rule for making ISMS changes in a planned way. | Change-planning step in the ISMS procedure. | Chief Technology Officer | ISO-08 | 31 Dec 2026 | no | Absent
7.1 | Resources | N | 1 | The budget is estimated in CGI-RSK-001. | Not approved; no allocation of staff time to the ISMS. | Approved budget and time allocation. | Chief Executive Officer | ISO-03 | 31 Oct 2026 | no | Partial
7.2 | Competence, with documented evidence | N | 0 | None on file. | No competence requirements for ISMS roles and no evidence of competence. | Role competence matrix; training and certificate records. | Head of People and Operations | ISO-10 | 31 Mar 2027 | no | Absent
7.3 | Awareness of policy, contribution and implications of non-conformance | N | 1 | Induction 60% complete; 60% acknowledgement. | Not all staff reached; no recurring programme (CG-04). | 100% acknowledgement; REC-09 curriculum records. | Head of People and Operations | REC-04; REC-09 | 31 Mar 2027 | no | Partial
7.4 | Internal and external communication | N | 1 | Policies published; CGI-POL-005 defines incident communications. | No ISMS communication plan (what, when, with whom, how). | Communication plan. | Chief Technology Officer | ISO-08 | 31 Dec 2026 | no | Partial
7.5 | Documented information: creation, updating and control | N | 1 | Every CGI policy has a document control block (version, owner, review date). | No procedure controlling records; no document register. | Document and record control procedure; ISMS document register. | Chief Technology Officer | ISO-08 | 31 Dec 2026 | no | Partial
8.1 | Operational planning and control, including control of externally provided processes | N | 1 | The CGI-TPR-001 workflow controls externally provided services. | Other operational processes are not planned or evidenced. | Operating records for the RTP actions. | Chief Technology Officer | ISO-06 | 31 Mar 2027 | no | Partial
8.2 | Perform risk assessments at planned intervals or on significant change; retain results | N | 2 | Performed September 2026 (v1.0) and again on change (v1.1 vendor addendum); results retained. | The planned interval is not yet defined (recorded under 6.1.2). | Next scheduled assessment record. | Chief Technology Officer | ISO-05 | 31 Oct 2026 | no | Met
8.3 | Implement the risk treatment plan; retain results | N | 1 | CGI-TPR-001 executed (CG-06 closed); AVD-001 and ACC-001 in force. | Most RTP actions not started (Wave 1 due Q4 2026). | Treatment status tracker with evidence per action. | Chief Technology Officer | ISO-06 | 31 Mar 2027 | no | Partial
9.1 | Monitoring, measurement, analysis and evaluation; retain results | N | 1 | 14 KRIs defined; KRI-V1 measured once (65%). | No monitoring programme; results not reported (GV.OV = 1). | Quarterly KRI and objective report. | Chief Technology Officer | ISO-07; REC-10 | 31 Mar 2027 | no | Partial
9.2.1 | Internal audit at planned intervals | Y | 0 | None. | No internal audit has ever been performed. There is no REC for it in CGI-GAP-001 (see RC-03). | Completed internal audit of all clauses and applicable controls before Stage 1. | Chief Executive Officer | ISO-12 | 31 May 2027 | YES | Absent
9.2.2 | Internal audit programme: frequency, methods, responsibilities, criteria and scope; auditor objectivity; results reported | Y | 0 | None. | No programme; no independent auditor identified. | Audit programme; audit plan; audit report. | Chief Executive Officer | ISO-12 | 31 Mar 2027 | YES | Absent
9.3.1 | Management review at planned intervals | Y | 0 | None. No security item has appeared on a leadership agenda (GAP-005). | Never held. | Minutes of management review #1 (Mar 2027) and #2 (Jun 2027). | Chief Executive Officer | ISO-13; REC-10 | 31 Mar 2027 | YES | Absent
9.3.2 | Management review inputs a) to g), including changes in interested parties' needs | Y | 0 | None. | The REC-10 agenda (KRIs, scorecard, TP status) omits several 9.3.2 inputs (see RC-02). | Agenda template covering 9.3.2 a) to g). | Chief Executive Officer | ISO-13 | 31 Mar 2027 | YES | Absent
9.3.3 | Management review results: improvement decisions and changes; documented | Y | 0 | None. | Never held. | Minutes with decisions and actions. | Chief Executive Officer | ISO-13 | 31 Mar 2027 | YES | Absent
10.1 | Continual improvement | N | 1 | Improvement happens through commissioned projects (ID.IM = 1). | No routine improvement loop. | Improvement log fed by audits, KRIs, incidents and exceptions. | Chief Technology Officer | ISO-08 | 31 Dec 2026 | no | Partial
10.2 | Nonconformity and corrective action (correction, root cause, action, effectiveness review); retained | N | 0 | CGI-POL-005 section 5.7 covers incident corrective actions only (a fragment). | No nonconformity process; exceptions (EXC-001 to -003) are not nonconformities. | NC and corrective action procedure and log. | Chief Technology Officer | ISO-08 | 31 Dec 2026 | no | Absent
Points |  |  | 19
Maximum |  |  | 56
Clause score |  |  | 33.93%
Gates |  |  | 8
Gates failed |  |  | 8

## 05_DocInfo
Mandatory documented information checklist
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Ref | Documented information | Required by | Status (Have/Partial/Missing) | What Cypher Group Inc. already has | What is missing | Owner (job title) | Due
DI-01 | ISMS scope | Clause 4.3 | Partial | CGI-ISO-001 section 2 (draft) | CEO approval | Chief Executive Officer | 31 Oct 2026
DI-02 | Information security policy | Clause 5.2 | Missing | None at ISMS level (CGI-POL-001 to -005 are topic-specific) | Top-level ISMS policy | Chief Executive Officer | 31 Oct 2026
DI-03 | Risk assessment process, including acceptance criteria | Clause 6.1.2 | Partial | CGI-RSK-001 methodology and thresholds | Risk acceptance criteria and appetite (GAP-002) | Chief Executive Officer | 31 Oct 2026
DI-04 | Risk treatment process | Clause 6.1.3 | Partial | CGI-RSK-001 treatment strategies (Mitigate, Transfer, Accept, Avoid) | Link to SoA and residual-acceptance step | Chief Technology Officer | 30 Nov 2026
DI-05 | Statement of Applicability | Clause 6.1.3 d) | Partial | CGI-ISO-001 section 3 (draft v1.0, 93 controls) | CEO approval | Chief Executive Officer | 30 Nov 2026
DI-06 | Risk treatment plan | Clause 6.1.3 e); 8.3 | Partial | CGI-RSK-001 TP-01 to TP-10; CGI-GAP-001 REC-01 to REC-18; CGI-TPR-001 R1-R8 and C1-C4; CGI-ISO-001 section 7 | One consolidated plan approved by the risk owners | Chief Executive Officer | 30 Nov 2026
DI-07 | Information security objectives | Clause 6.2 | Missing | None (the KRIs are inputs) | Objectives with measures and dates | Chief Technology Officer | 30 Nov 2026
DI-08 | Evidence of competence | Clause 7.2 d) | Missing | None | Competence matrix and records | Head of People and Operations | 31 Mar 2027
DI-09 | Documented information the organisation decides is necessary | Clause 7.5.1 b) | Partial | CGI policy document control blocks | Document register and control procedure | Chief Technology Officer | 31 Dec 2026
DI-10 | Operational planning and control records | Clause 8.1 | Partial | CGI-TPR-001 workflow and records | Records for the other RTP processes | Chief Technology Officer | 31 Mar 2027
DI-11 | Results of risk assessments | Clause 8.2 | Have | CGI-RSK-001 v1.0 and v1.1 (VR-001 to VR-009 addendum) | Next scheduled run | Chief Technology Officer | 31 Oct 2026
DI-12 | Results of risk treatment | Clause 8.3 | Partial | CGI-TPR-001 (CG-06 closed); ACC-001; ACC-V01; AVD-001 | Evidence for each RTP action | Chief Technology Officer | 31 Mar 2027
DI-13 | Monitoring and measurement results | Clause 9.1 | Partial | KRI-V1 measured once (65%) | Quarterly results for all KRIs and objectives | Chief Technology Officer | 31 Mar 2027
DI-14 | Audit programme and audit results | Clause 9.2.2 | Missing | None | Programme, plan and report | Chief Executive Officer | 31 May 2027
DI-15 | Management review results | Clause 9.3.3 | Missing | None | Minutes of two reviews before Stage 1 | Chief Executive Officer | 30 Jun 2027
DI-16 | Nonconformities, actions taken and corrective action results | Clause 10.2 | Missing | None (EXC register is not an NC log) | NC and corrective action log | Chief Technology Officer | 31 Dec 2026
DI-17 | Topic-specific policies | A.5.1 | Partial | CGI-POL-001 to -005 | CGI-POL-006 Backup, -007 Secure Development, -008 Vulnerability Management; cryptography standard | Chief Technology Officer | 31 Mar 2027
DI-18 | Inventory of information and other associated assets | A.5.9 | Partial | CGI-TPR-001 vendor inventory (17) | Asset and SaaS inventory (REC-05) | IT Operations Manager | 31 Mar 2027
DI-19 | Rules for acceptable use | A.5.10 (control text says documented) | Have | CGI-POL-001 v1.0 | Acknowledgement to 100% | Head of People and Operations | 31 Dec 2026
DI-20 | Legal, statutory, regulatory and contractual requirements | A.5.31 (control text says documented) | Missing | None | Obligations register | Chief Executive Officer | 31 Oct 2026
DI-21 | Documented operating procedures | A.5.37 (control text says documented) | Missing | None beneath the policies | Runbooks (REC-12) | IT Operations Manager | 30 Jun 2027
DI-22 | Confidentiality or non-disclosure agreements | A.6.6 (control text says documented) | Missing | None on file | Signed NDAs | Head of People and Operations | 31 Dec 2026
DI-23 | Configurations, including security configurations | A.8.9 (control text says documented) | Missing | None | CIS-based baseline (REC-11) | IT Operations Manager | 30 Jun 2027
DI-24 | Incident management plan and procedures | A.5.24 / A.5.26 (auditor-expected) | Have | CGI-POL-005 v1.0 | Exercise record; runbooks | Chief Technology Officer | 30 Jun 2027
DI-25 | ICT continuity plan with RTO and RPO | A.5.30 (auditor-expected) | Missing | None | CGI-POL-006 and restore test (REC-03) | IT Operations Manager | 15 Dec 2026
DI-26 | Supplier security procedure and supplier register | A.5.19 to A.5.22 (auditor-expected) | Have | CGI-TPR-001 v1.0; CGI-TPR-002 | Review records on cadence | Chief Technology Officer | 30 Sep 2027
DI-27 | Record of processing activities | GDPR Art. 30 (legal, via A.5.34) | Missing | None (out of scope in CGI-GAP-001) | Article 30 record | Chief Technology Officer | 31 Dec 2026
| Have |  | 4
| Partial |  | 11
| Missing |  | 12
| Total |  | 27

## 06_Readiness
Certification readiness score and Stage 1 go/no-go
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Element | Value | Note
Clause score (04_Clauses) | 33.93% | Sum of 0-2 scores / maximum
Annex A score (03_SoA_Summary) | 25.57% | (Implemented x1 + Partial x0.5) / applicable
Weight - clauses | 60% | Input. Clauses cannot be excluded and carry most first-certification majors
Weight - Annex A | 40% | Input
Weights check | PASS | Weights must sum to 100%
Weighted readiness | 30.58%
Gate requirements | 8 | 4.3, 6.1.2, 6.1.3, 9.2.1, 9.2.2, 9.3.1, 9.3.2, 9.3.3
Gates failed | 8 | Any failed gate forces NO-GO
Band threshold - ready | 85% | Input
Band threshold - within 90 days | 60% | Input
Band | Not ready
Stage 1 decision today | NO-GO | Gate override applied first
Realistic certification date | Nov 2027 | Stage 1 Jul 2027 -> Stage 2 Oct 2027 -> certificate Nov 2027 (see 07_Roadmap)

## 07_Roadmap
Prioritised roadmap to certification (costs are planning estimates, ISO-A05)
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
ID | Action | Clause / control | Owner (job title) | Start | Due | Phase | Est. cost (USD) | Dependency | Notes
ISO-01 | Context, interested parties and obligations register (including the climate-change relevance decision) | 4.1; 4.2; A.5.31 | Chief Executive Officer | 01 Oct 2026 | 31 Oct 2026 | Phase 0 - Foundation | 0 | None | Would support GV.OC 1 -> 2 once approved
ISO-02 | Approve the ISMS scope and boundary, including the AWS shared-responsibility statement | 4.3; A.5.23; A.8.27 | Chief Executive Officer | 01 Oct 2026 | 31 Oct 2026 | Phase 0 - Foundation | 0 | ISO-01 | Takes the documentation half of REC-18 forward (RC-04)
ISO-03 | ISMS policy v1.0; approve the USD 32,100 year-one budget and ISMS time allocation | 5.1; 5.2; 7.1 | Chief Executive Officer | 01 Oct 2026 | 31 Oct 2026 | Phase 0 - Foundation | 0 | ISO-01 | One page, signed by the CEO
ISO-04 | Assign the ISMS lead (CTO) and publish the ISMS RACI | 5.3; A.5.2 | Chief Executive Officer | 01 Oct 2026 | 31 Oct 2026 | Phase 0 - Foundation | 0 | None | Implements the GAP-003 recommended action
ISO-05 | Risk acceptance criteria and appetite; annual plus event-driven assessment cadence | 6.1.2; 8.2 | Chief Executive Officer | 01 Oct 2026 | 31 Oct 2026 | Phase 0 - Foundation | 0 | None | Same work as REC-13, pulled forward from Q2 2027 (RC-01)
ISO-06 | Approve SoA v1.0 and one consolidated risk treatment plan; risk owners sign residual acceptance for R-004, R-005 and VR-004 | 6.1.3; 8.1; 8.3 | Chief Executive Officer | 01 Nov 2026 | 30 Nov 2026 | Phase 1 - Plan | 0 | ISO-05 | Without ISO-05 these acceptances have no criteria to be made against
ISO-07 | ISMS objectives and measurement plan built on the 14 KRIs | 6.2; 9.1 | Chief Technology Officer | 01 Nov 2026 | 30 Nov 2026 | Phase 1 - Plan | 0 | ISO-06 | Example objective: KRI-V1 (DPA coverage) at 100% and held there every quarter
ISO-08 | ISMS procedures: document and record control, change planning, communication, ISMS risks and opportunities, NC and corrective action, improvement log | 4.4; 6.1.1; 6.3; 7.4; 7.5; 10.1; 10.2 | Chief Technology Officer | 01 Nov 2026 | 31 Dec 2026 | Phase 1 - Plan | 0 | ISO-03 | One short procedure document
ISO-09 | Execute the six outstanding DPAs; approve the CGI-POL-004 section 4.2 amendment; build the GDPR Art. 30 record of processing | A.5.14; A.5.20; A.5.34 | Chief Technology Officer | 01 Oct 2026 | 31 Dec 2026 | Phase 1 - Plan | 0 | None | DPAs by 31 Oct 2026 (CGI-TPR-001 30-day ask); record of processing by 31 Dec 2026
ISO-10 | Competence matrix and records; CTO completes ISO/IEC 27001 Lead Implementer training | 7.2 | Head of People and Operations | 01 Jan 2027 | 31 Mar 2027 | Phase 2 - Build | 2500 | ISO-04 | Training cost is a planning estimate
ISO-11 | People, physical and residual technical baseline: screening, terms, disciplinary, NDAs, office rules, malware, masking, web filtering, cryptography, capacity, licences, audit-testing rules | A.6.1-A.6.6; A.7.x; A.8.6; A.8.7; A.8.11; A.8.14; A.8.23; A.8.24; A.5.32; A.8.34 | Head of People and Operations | 01 Jan 2027 | 30 Jun 2027 | Phase 2 - Build | 0 | ISO-03 | Staff time; owners per SoA row
ISO-12 | Internal audit programme; independent internal audit of clauses 4-10 and all applicable controls | 9.2; A.5.35 | Chief Executive Officer | 01 Mar 2027 | 31 May 2027 | Phase 3 - Check | 6000 | ISO-06 | Planning estimate for ~4-5 external auditor days; auditor must not audit their own work
ISO-13 | Management review #1 (Mar 2027) and #2 (Jun 2027, after the internal audit), using the REC-10 forum with the full 9.3.2 agenda | 9.3 | Chief Executive Officer | 01 Mar 2027 | 30 Jun 2027 | Phase 3 - Check | 0 | ISO-07; ISO-12 | Same forum as REC-10, with an extended agenda (RC-02)
ISO-14 | Select an accredited certification body (check the DAkkS/UKAS mark and scope); fix audit days; book Stage 1 and Stage 2 | Certification | Chief Executive Officer | 01 Jan 2027 | 31 Mar 2027 | Phase 2 - Build | 0 | ISO-02 | Selection itself is free; fees in ISO-17
ISO-15 | Corrective actions from the internal audit and Stage 1 | 10.2 | Chief Technology Officer | 01 Jun 2027 | 31 Aug 2027 | Phase 4 - Audit | 0 | ISO-12 | Staff time
ISO-16 | Purchase ISO/IEC 27001:2022 (+Amd 1) and ISO/IEC 27002:2022 | Support | Chief Technology Officer | 01 Oct 2026 | 15 Oct 2026 | Phase 0 - Foundation | 400 | None | Planning estimate
ISO-17 | Certification audit: Stage 1 (Jul 2027) and Stage 2 (Oct 2027, after the Tier 1 vendor re-reviews due Sep 2027) | Certification | Chief Executive Officer | 01 Jul 2027 | 31 Oct 2027 | Phase 4 - Audit | 14000 | ISO-12; ISO-13; ISO-14 | Planning estimate for a 50-person single-site scope; certificate expected Nov 2027
| ISO-specific cost to certificate | [5 empty] | 22900
| Year-one security budget already costed (CGI-RSK-001) | [5 empty] | 32100
| Programme cost to certificate | [5 empty] | 55000
| ARR (CGI-RSK-001 assumption A-01) | [5 empty] | 3600000
| Programme cost as % of ARR | [5 empty] | 1.528%
| Annual surveillance audit from 2028 (estimate) | [5 empty] | 7000

## 08_REC_Reconciliation
CGI-GAP-001 REC-01 to REC-18 reconciled against the certification plan
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
REC | Recommendation (CGI-GAP-001) | GAP quarter | ISO clause / control served | Latest date ISO needs it | Conflict? | Resolution
REC-01 | MFA to 100%; retire ACC-001 | Q4 2026 | A.5.17; A.8.5 | Before Stage 1 | No | Keep.
REC-02 | First quarterly privileged access review | Q4 2026 | A.5.18; A.8.2 | 4 quarterly records by Stage 2 | No | Keep; the Dec 2026, Mar, Jun and Sep 2027 reviews give four samples.
REC-03 | Restore test; CGI-POL-006 with RTO/RPO | Q4 2026 | A.8.13; A.5.30 | Before Stage 1 | No | Keep; same work as VRA-2026-001 C4 (15 Dec 2026) - do not run it twice.
REC-04 | Acknowledgement 60% -> 100%; joiner gate | Q4 2026 | A.5.1; A.5.4; 7.3 | Before Stage 1 | No | Keep.
REC-05 | Asset and SaaS inventory | Q1 2027 | A.5.9; A.5.12; A.5.13; A.8.1 | Before Stage 1 | No | Keep. Note: REC-15 was delivered before its REC-05 dependency; the vendor inventory is an input, not a substitute.
REC-06 | CGI-POL-007; branch protection with peer review | Q1 2027 | A.8.25; A.8.28; A.8.31; A.8.32; A.8.3; A.8.4 | Operating for 2+ quarters before Stage 2 | No - but a hard deadline | Keep Q1 2027 and treat it as immovable: any slip moves the certificate date.
REC-07 | CloudTrail, central logs, alerting | Q1 2027 | A.8.15; A.8.16; A.8.17; A.5.28 | Before Stage 1 | No | Keep.
REC-08 | CGI-POL-008; authenticated scanning | Q1 2027 | A.8.8; A.5.7 | Operating for 2+ quarters before Stage 2 | No | Keep.
REC-09 | Awareness curriculum; phishing simulation | Q1 2027 | A.6.3; 7.3 | Before Stage 1 | No | Keep.
REC-10 | Quarterly security review with the CEO | Q1 2027 | 9.3; 9.1 | MR #1 by Mar 2027 | PARTIAL (RC-02) | The REC-10 agenda (KRIs, scorecard, TP status) is not a full clause 9.3 review. Extend it to the 9.3.2 a) to g) inputs and minute it as the management review.
REC-11 | CIS AWS baseline; posture monitoring | Q2 2027 | A.8.9; A.8.20; A.8.21 | Before Stage 2 | No - tight | Keep Q2 2027; it gives only one quarter of evidence before Stage 2. Start in April, not June.
REC-12 | SEV1 tabletop; lessons learned | Q2 2027 | A.5.24; A.5.26; A.5.27; A.6.8 | Before Stage 1 | No | Keep; schedule the tabletop in April 2027 so lessons feed MR #2.
REC-13 | Risk appetite; assessment cadence | Q2 2027 | 6.1.2 a) acceptance criteria | Before SoA and RTP approval (Nov 2026) | YES (RC-01) | Pull forward to 31 Oct 2026 as ISO-05. Remove the REC-10 dependency: the CEO approves directly, and the approval is ratified at MR #1.
REC-14 | Customer recovery communication pack; status page | Q2 2027 | A.5.29; A.5.5 | Before Stage 2 | No | Keep; CGI-VEN-017 onboarding under way.
REC-15 | Tiered vendor inventory; DPAs; section 4.2 amendment | Q2 2027 | A.5.19 to A.5.23 | Delivered | STATUS CHANGE (RC-05) | Delivered 15 Sep 2026 by CGI-TPR-001, three quarters early. The outstanding DPAs and section 4.2 approval move to ISO-09.
REC-16 | SAST in CI; annual penetration test | Q3 2027 | A.8.29; A.8.3 | RTP-dated at Stage 2 is acceptable | No | Keep; run the test in Aug 2027 so the report is available at Stage 2.
REC-17 | Data egress and DLP monitoring | Q3 2027 | A.8.12; A.8.10 | RTP-dated at Stage 2 is acceptable | No | Keep.
REC-18 | Segmentation; production boundary; shared-responsibility boundary | Q4 2027 | A.8.22; A.8.27; A.5.23 | Boundary needed for scope (Oct 2026) | YES (RC-04) | Split: the shared-responsibility boundary moves to ISO-02 (Oct 2026); segmentation remediation stays in Q4 2027 in the RTP, with R-005 residual accepted under ISO-05.
ID | Conflict | Why it matters | Resolution
RC-01 | REC-13 (Q2 2027) versus clause 6.1.2 a) | Risk acceptance criteria are a prerequisite of the SoA and RTP approval, not a Q2 2027 improvement. | REC-13 becomes ISO-05, due 31 Oct 2026.
RC-02 | REC-10 versus clause 9.3.2 | A quarterly security review is not automatically a management review. | Extend the agenda to inputs a) to g); minute it as the management review (ISO-13).
RC-03 | No internal audit anywhere in REC-01 to REC-18 | An omission in CGI-GAP-001, not a contradiction. Clause 9.2 cannot be excluded. | New action ISO-12.
RC-04 | REC-18 (Q4 2027) falls after Stage 2 | The scope statement needs the AWS boundary now. | Split: documentation to ISO-02 (Oct 2026); segmentation remains Q4 2027 in the RTP.
RC-05 | REC-15 shows Q2 2027 but was delivered Sep 2026 | A stale status, not a contradiction. | Mark delivered; leftovers to ISO-09.
RC-06 | Which control-gap ID sits behind PR.PS | Citing the wrong gap ID breaks the trace from the SoA back to the register. | CGI-RSK-001 section 4.3: CG-02 is secure development and vulnerability management, CG-04 is awareness training. CG-02 is used throughout.
Conflicts flagged YES |  | 2

## 09_GAP_Impact
Effect on CGI-GAP-001 maturity - no Category moves in Project 5
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Column F (after Project 5) is what 02_SoA uses for the maturity consistency check.
Ref | Category | Name | v1.0 (15 Sep 2026) | After Project 4 | After Project 5 | Target | Gap (target - after P5) | Moved in P5?
GAP-001 | GV.OC | Organizational Context | 1 | 1 | 1 | 2 | 1 | No
GAP-002 | GV.RM | Risk Management Strategy | 2 | 2 | 2 | 3 | 1 | No
GAP-003 | GV.RR | Roles, Responsibilities and Authorities | 2 | 2 | 2 | 3 | 1 | No
GAP-004 | GV.PO | Policy | 2 | 2 | 2 | 3 | 1 | No
GAP-005 | GV.OV | Oversight | 1 | 1 | 1 | 3 | 2 | No
GAP-006 | GV.SC | Cybersecurity Supply Chain Risk Management | 0 | 2 | 2 | 2 | 0 | No
GAP-007 | ID.AM | Asset Management | 1 | 1 | 1 | 3 | 2 | No
GAP-008 | ID.RA | Risk Assessment | 3 | 3 | 3 | 3 | 0 | No
GAP-009 | ID.IM | Improvement | 1 | 1 | 1 | 2 | 1 | No
GAP-010 | PR.AA | Identity Management, Authentication and Access Control | 2 | 2 | 2 | 3 | 1 | No
GAP-011 | PR.AT | Awareness and Training | 1 | 1 | 1 | 3 | 2 | No
GAP-012 | PR.DS | Data Security | 2 | 2 | 2 | 3 | 1 | No
GAP-013 | PR.PS | Platform Security | 0 | 0 | 0 | 3 | 3 | No
GAP-014 | PR.IR | Technology Infrastructure Resilience | 0 | 0 | 0 | 3 | 3 | No
GAP-015 | DE.CM | Continuous Monitoring | 1 | 1 | 1 | 3 | 2 | No
GAP-016 | DE.AE | Adverse Event Analysis | 1 | 1 | 1 | 2 | 1 | No
GAP-017 | RS.MA | Incident Management | 2 | 2 | 2 | 3 | 1 | No
GAP-018 | RS.AN | Incident Analysis | 1 | 1 | 1 | 2 | 1 | No
GAP-019 | RS.CO | Incident Response Reporting and Communication | 2 | 2 | 2 | 3 | 1 | No
GAP-020 | RS.MI | Incident Mitigation | 1 | 1 | 1 | 2 | 1 | No
GAP-021 | RC.RP | Incident Recovery Plan Execution | 1 | 1 | 1 | 3 | 2 | No
GAP-022 | RC.CO | Incident Recovery Communication | 0 | 0 | 0 | 2 | 2 | No
|  | SUM | 27 | 29 | 29 | 59 | 30
|  | OVERALL AVERAGE (/22) | 1.2273 | 1.3182 | 1.3182 | 2.6818 | 1.3636
|  | Categories moved in Project 5 | [5 empty] | 0
|  | Projection: GV.OC 1 -> 2 when ISO-01/ISO-02 are approved |  |  | 1.3636

## 10_Assumptions
Assumptions and candidate risks
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
ID | Assumption | Why it matters
ISO-A01 | Cypher Group Inc. operates from a single head office. Its address is not defined in Projects 1-4, so the certificate line carries a bracketed address field. | Projects 1-4 never state a location; a real certificate must.
ISO-A02 | All software development is performed by CGI employees; no contractor or agency writes code. | Basis for excluding A.8.30. Re-include before any outsourcing.
ISO-A03 | The head office is a leased serviced office whose landlord operates building entry control and fire safety; there is no server or network room. | Basis for excluding A.7.4, A.7.6, A.7.11 and A.7.12.
ISO-A04 | Customers depend on platform availability commercially; no contractual SLA figure is recorded in Projects 1-4. | Basis for including A.8.6 on a stakeholder rather than a risk basis.
ISO-A05 | ISO-specific costs are planning estimates for a 50-person single-site scope, not quotes. | Obtain three certification-body quotes in ISO-14.
ISO-A06 | The Project 4 approval of CGI-TPR-001 by the CEO is treated as the approval of the supplier procedure. | Required for GV.SC = 2 and for A.5.19 to A.5.22 at maturity 2.
ID | Candidate risk (for next CGI-RSK-001 review - NOT added) | Controls it would justify | Why only a candidate
CR-01 | Lost or stolen endpoint exposes Confidential data | A.7.9; A.8.1; A.8.24 | No CGI-RSK-001 risk covers device loss on a BYOD estate of 50.
CR-02 | Platform capacity exhaustion causes a customer-facing outage | A.8.6; A.8.14 | Availability is covered only for ransomware (R-002) and vendor concentration (VR-002).
CR-03 | Unauthorised physical access to the office | A.7.1; A.7.2; A.7.3 | Physical security was out of scope in CGI-GAP-001.

## 11_Issue_Checklist
Issue checklist - quality gates
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
# | Check | Result | How verified
1 | 93 controls in 02_SoA | PASS | Formula
2 | Theme counts 37/8/14/34 | PASS | Formula
3 | Implemented + Partial + Not started = applicable | PASS | Formula
4 | No control maturity above its highest related Category | PASS | Formula (02_SoA column S)
5 | Seven PR.PS-linked controls (A.5.7, A.8.8, A.8.25, A.8.28, A.8.29, A.8.31, A.8.32) Not started | PASS | Formula
6 | A.5.19 to A.5.23 not Implemented (GV.SC = 2) | PASS | Formula
7 | Readiness weights sum to 100% | PASS | Formula
8 | Document checklist totals 27 | PASS | Formula
9 | Every applicable control traced to a risk, Category or finding, or labelled NOT risk-based | PASS | Python check
10 | All 14 risk IDs and findings F-001 to F-013 and O-001 referenced | PASS | Python check
11 | REC-01 to REC-18 all reconciled | PASS | Python check
12 | CGI-GAP-001 sums 27 / 29 / 29, target 59; averages 1.23 / 1.32 / 1.32 / 2.68 | PASS | Formula
13 | Owners are job titles, never named individuals | PASS | Python check
14 | Target dates all after 16 Sep 2026 | PASS | Python check
15 | Case-study notice on every sheet | PASS | Row 2 of every sheet
16 | No merged cells; one value per cell | PASS | Build script
17 | Zero formula errors after LibreOffice recalculation | PASS | LibreOffice recalculation before delivery
18 | Every control the CGI-POL pack maps in its own framework tables (38) is credited or named as a fragment | PASS | Python check

## 12_Lists
Validation lists
SIMULATED CASE STUDY - Cypher Group Inc. is a simulated company. CGI-ISO-001 v1.0, 16 Sep 2026. Prepared by O.S; for approval by Jerry Olugboye.
Applicable | Status | Doc status | Owner (job title)
Y | Not started | Have | Chief Executive Officer
N | Partial | Partial | Chief Technology Officer
| Implemented | Missing | Head of People and Operations
| N/A - excluded |  | IT Operations Manager
Head of Customer Success
Finance Manager